## Backlog Creation
Backlog Creation (Tasks from User Stories)
Module | Task ID | Task Description
Login Module | Task 1 | Develop user login screen (UI/UX).
| Task 2 | Implement backend authentication (username, password, OTP).
| Task 3 | Set up error handling for invalid login attempts.
| Task 4 | Integrate two-factor authentication (2FA).
| Task 5 | Write unit tests for login functionality.
Account Management | Task 6 | Develop user dashboard to display account balance.
| Task 7 | Create API to retrieve and update user details.
| Task 8 | Implement account settings (e.g., password reset).
| Task 9 | Test account data consistency across multiple sessions.
Fund Transfer Module | Task 10 | Design transfer interface (recipient details, amount, etc.).
| Task 11 | Implement fund transfer logic (IMPS/NEFT/UPI).
| Task 12 | Validate input data (amount limits, recipient account).
| Task 13 | Ensure transaction notifications.
| Task 14 | Write automated tests for fund transfer flow.
Payment Module | Task 15 | Develop bill payment page (electricity, water, etc.).
| Task 16 | Integrate with payment gateways.
| Task 17 | Implement scheduled and recurring payments.
| Task 18 | Add feature to download payment receipts.
Report Module | Task 19 | Create transaction history view.
| Task 20 | Implement filtering by date, type, and amount.
| Task 21 | Export reports in PDF/CSV formats.
| Task 22 | Write performance tests for generating reports.

## Sprint Planning
Sprint Planning
Sprint | Goal | Tasks Included
Sprint 1 | Develop Login and Account Management | Task 1, Task 2, Task 6, Task 8
Example: Develop login UI and backend authentication.
Sprint 2 | Implement Fund Transfer Functionality | Task 10, Task 11, Task 12, Task 13
Example: Build transfer logic and transaction notifications.
Sprint 3 | Complete Payment Module and Reports | Task 15, Task 16, Task 19, Task 21
Example: Set up bill payments and export reports.

## Sprint Execution
Sprint Execution
Sprint | Tasks | Acceptance Criteria
Sprint 1 | Task 1: Login screen (UI/UX) | UI follows design guidelines and is functional.
| Task 2: Backend authentication setup | Users can log in using credentials and 2FA.
| Task 6: User dashboard development | Dashboard displays account balances accurately.
| Task 8: Account settings implementation | Password reset functionality works as expected.
Sprint 2 | Task 10: Transfer interface design | Users can enter recipient details and amount easily.
| Task 11: Fund transfer logic | Transfers complete successfully via IMPS/NEFT/UPI.
| Task 12: Input validation | Error shown if transfer exceeds balance or input is invalid.
| Task 13: Transaction notifications | Notifications are sent for success/failure transactions.
Sprint 3 | Task 15: Bill payment page | Users can view and pay bills through the interface.
| Task 16: Payment gateway integration | Payments are processed securely through gateways.
| Task 19: Transaction history view | Users can filter and view their transaction history.
| Task 21: Export reports | Users can download reports in PDF/CSV formats.

## Release Planning
Release Planning
Release | Scope | Timeline
First Release | Login Module (user authentication, 2FA) | After Sprint 1
Account Management (dashboard, account settings)
Second Release | Fund Transfer (basic transfer functionality) | After Sprint 2
Third Release | Payment Module (bill payments) and Report Module (history view) | After Sprint 3

## Explanation
Detailed Explanation of the Sprint Review, Scrum, Retrospective, Release Planning, Roles
Term | Description | Purpose | Example
Sprint Review | - Meeting held at the end of each sprint. | - Ensure that completed tasks meet the requirements. | Sprint 1 Review: Confirm that login and account management functionalities are working as expected and ready for the next stage.
| - The team reviews completed tasks and features. | - Align progress with stakeholder expectations and adjust if needed.
- Identify if any changes are needed to align with the project goals.
Scrum | - Daily meetings (15 minutes) attended by the development, testing, and operations teams. | - Track daily progress. | During the daily Scrum meeting, a developer reports a blocker on backend authentication, which is quickly assigned to a team member for resolution.
| - Discuss what was completed, what is planned, and any roadblocks encountered. | - Identify blockers early and ensure all team members stay aligned.
Sprint Retrospective | - A meeting held at the end of each sprint. | - Focus on continuous improvement in processes. | After Sprint 1, the team realizes that they need to improve communication to catch blockers earlier. This insight helps them avoid delays in Sprint 2.
| - The team reflects on what went well, what didn’t, and how to improve future sprints. | - Identify ways to eliminate inefficiencies and blockers.
Release Planning | - Planning the scope of the first and subsequent releases of the product. | - Ensure that the most critical features are prioritized for early delivery. | For the first release, include login, account management, and fund transfer functionalities. Schedule the release for 4 weeks from now.
| - Identify features to be included in the MVP (Minimum Viable Product). | - Provide clarity on timelines to stakeholders.
- Set timelines for the release.
Roles in Scrum | - Product Owner: Manages the product backlog and ensures priorities align with the business vision. | - Clearly defines roles to avoid confusion. | The Product Owner prioritizes the login feature, while the Development Team implements it. The Testing Team verifies that the feature works correctly before release.
| - Business Analyst: Gathers and refines requirements from stakeholders. | - Ensures smooth collaboration across teams.
- Managers: Oversee the overall project and ensure alignment with goals.
- Tech Architect: Designs the technical architecture of the app.
- Development Team: Codes and implements the features.
- Testing Team: Ensures the product meets quality standards.
- Operations Team: Manages deployment and app maintenance.